## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency
S1 | S1 | US-001 | Introduction to project(Form Filling AI) | MUST HAVE | No Dependency
S1 | S1 | US-001 | Workflow Creation and Project Goal Document | MUST HAVE | Lucid Chart
S2 | S2 | US-001 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | No Dependency
S2 | S2 | US-001 | Use Case Research and Preparation | SHOULD HAVE | Gemini
S3 | S3 | US-001 | Python practice Kit Completion | MUST HAVE | HackerRank
S4 | S4 | US-001 | SQL practice Kit Completion | MUST HAVE | HackerRank
S5 | S5 | US-001 | Project Discussion Module 1(Voice Input and Language Processing) | MUST HAVE | Gemini and Assembly AI
S6 | S6 | US-001 | Project Discussion Module 2(Workflow Automation and Optimization) | SHOULD HAVE | VS Code
S7 | S7 | US-001 | Project Discussion Module 3(Integration with existing services) | SHOULD HAVE | Express.js for Backend
S8 | S8 | US-001 | Project Discussion Module 4(Frontend UI Development) | MUST HAVE | Render
S9 | S9 | US-001 | Project Discussion Module 5(Database Management) | SHOULD HAVE | React.js for Frontend
S10 | S10 | US-001 | Project Discussion Module 6(Testing & Deployment) | MUST HAVE | Vercel & Render
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[7 empty] | 80 | 20 | 11 | 11 | 14 | 8 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project(Form Filling AI) | 2025-02-07 | 2025-02-10 | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow Creation and Project Goal Document | 2025-02-11 | 2025-02-12 | Design | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2025-02-13 | 2025-02-13 | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Use Case Research and Preparation | 2025-02-13 | 2025-02-14 | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Python practice Kit Completion | 2025-02-14 | 2025-02-15 | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | SQL practice Kit Completion | 2025-02-14 | 2025-02-15 | Coding | 3- Completed | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Project Discussion Module 1(Voice Input and Language Processing) | 2025-02-17 | 2025-02-20 | Build | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Project Discussion Module 2(Workflow Automation and Optimization) | 2025-02-20 | 2025-02-23 | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Project Discussion Module 3(Integration with existing services) | 2025-02-24 | 2025-02-27 | Integration Test | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Project Discussion Module 4(Frontend UI Development) | 2025-02-28 | 2025-03-04 | Design | 3- Completed | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | Project Discussion Module 5 (Database Management) | 2025-03-05 | 2025-03-09 | Coding | 3- Completed | 10 | 0 | 0 | 0 | 4 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | Project Discussion Module 6 (Testing & Deployment) | 2025-03-10 | 2025-03-12 | System Test | 3- Completed | 8 | 0 | 0 | 2 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 13 | Presentation Making | 2025-03-12 | 2025-03-14 | Design | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on H3: This is the total task estimated in hours for all the user stories
Note on I3: Pending effort hours after completion of day 1 work
Note on J3: Pending effort hours after completion of day 2 work
Note on K3: Pending effort hours after completion of day 3 work
Note on L3: Pending effort hours after completion of day 4 work
Note on M3: Pending effort hours after completion of day 5 work
Note on N3: Pending effort hours after completion of day 6 work
Note on O3: Pending effort hours after completion of day 7 work
Note on P3: Pending effort hours after completion of day 8 work
Note on Q3: Pending effort hours after completion of day 9 work
Note on R3: Pending effort hours after completion of day 10 work
Note on S3: Pending effort hours after completion of day 11 work
Note on T3: Pending effort hours after completion of day 12 work
Note on U3: Pending effort hours after completion of day 13 work
Note on V3: Pending effort hours after completion of day 14 work

## Stand Up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unclear functional requirements for voice input and multilingual support. | Conducted a team session to refine feature scope and consulted industry references.
Sprint 1 | Day 5 | Issues in integrating voice-to-text processing with form fields. | Researched speech recognition APIs and tested alternative solutions.
Sprint 2 | Day 8 | Delay in frontend development due to complex UI interactions. | Collaborated with UI/UX team to optimize workflow and simplify interactions.
Sprint 2 | Day 10 | API response time lagging, causing slow form submission. | Optimized API calls and introduced asynchronous data processing.
Sprint 3 | Day 15 | Difficulty in implementing real-time error correction. | Integrated an AI-based error detection mechanism and refined the correction model.
Sprint 3 | Day 18 | Security concerns with user data handling. | Implemented data encryption and reviewed compliance measures.
Sprint 4 | Day 20 | Unexpected bugs in backend deployment. | Conducted a debugging sprint and refined error logs.

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2025-02-17 | 2025-02-20 | Team Collaboration | Researching voice recognition models | Assuming default speech-to-text works well | Engaging in team discussions | Conducted a review session on optimal models for voice input processing
2 | Sprint 2 | 2025-02-28 | 2025-03-04 | Team Collaboration | Implementing frontend integration for voice-enabled form | Delaying API integration | Debugging minor UI glitches | Successfully integrated basic voice input with form fields
3 | Sprint 3 | 2025-02-24 | 2025-02-27 | Team Collaboration | Optimizing voice-to-text accuracy | Ignoring user accent variations | Refining dataset for model training | Collected multilingual voice samples for improved model training
4 | Sprint 4 | 2025-03-10 | 2025-03-12 | Team Collaboration | Testing real-time error correction | Relying only on predefined commands | Analyzing user interaction flow | Improved error correction using AI-based predictions
5